## Smart Media Estimation Sheet
SL No | TASKS | RESOURCES | LINES OF CODE | MODEL | DECISION | PERSON DAYS
| Planning | Angad | N/A | Delphi | All agreed | 24
1 | Prepare Project Plan | Angad | N/A | Delphi | All agreed | 10
2 | Submit and get approval for Project Plan | Angad | N/A | Delphi | All agreed | 5
3 | Decide on hardware and software requirements | Angad | N/A | Delphi | All agreed | 4
4 | Resource Planning | Angad | N/A | Delphi | All agreed | 4
5 | Project Kick-off Meeting | Angad | N/A | Delphi | All agreed | 1
| Analysis and Preparation phase | Ankita,Hao,Thanos,Jo,Athina,Angad | N/A | Delphi | All agreed | 19
6 | Create FRS from BRS | Jo,Athina | N/A | Delphi | All agreed | 7
7 | FRS signed and approved | Jo,Athina | N/A | Delphi | All agreed | 5
8 | Risk Analysis | Angad,Jo,Athina | N/A | Delphi | All agreed | 5
9 | Software and Hardware configuration | Ankita,Hao,Thanos,Athina | N/A | Delphi | All agreed | 2
| Design Phase | Ankita,Athina,Jo,Thanos,Hao | N/A | Delphi | All agreed | 28
10 | Design of HLD and LLD from FRS | Ankita,Athina,Jo | N/A | Delphi | All agreed | 20
11 | Knowledge Transfer Sessions | Ankita,Athina,Jo,Thanos,Hao | N/A | Delphi | All agreed | 8
| DB Setup | Thanos | 500 | COCOMO | Intermediate | 3*0.5^1.12
12 | Create and Initialize customized tables | Thanos | 300 | COCOMO | Simple | 2.4*0.3^1.05
13 | DB Access Rights | Thanos | 50 | COCOMO | Simple | 2.4*0.05^1.05
14 | Testing of DB Setup | Thanos | 150 | COCOMO | Intermediate | 3*0.15^1.12
| WebSite Design for Customers/Business Users/Third Party Users | Ankita,Hao,Athina | 3530 | COCOMO | Intermediate | 3*3.53^1.12
15 | Access Rights Setup for Agents/Customers | Ankita,Hao,Athina | 80 | COCOMO | Intermediate | 3*0.08^1.12
16 | Development of Registration Form (Mandate Registration) | Ankita,Hao,Athina | 300 | COCOMO | Simple | 2.4*0.3^1.05
17 | Development of Home Page | Ankita,Hao,Athina | 400 | COCOMO | Simple | 2.4*0.4^1.05
18 | Development of Funding/Payment History Interface | Ankita,Hao,Athina | 300 | COCOMO | Intermediate | 3*0.3^1.12
19 | Development of Help component | Ankita,Hao,Athina | 250 | COCOMO | Simple | 2.4*0.25^1.05
20 | Development of Claim webpage | Ankita,Hao,Athina | 300 | COCOMO | Intermediate | 3*0.3^1.12
21 | Development of Dispute webpage | Ankita,Hao,Athina | 300 | COCOMO | Intermediate | 3*0.3^1.12
22 | Development of Search webpage | Ankita,Hao,Athina | 350 | COCOMO | Intermediate | 3*0.35^1.12
23 | Development of Query Page | Ankita,Hao,Athina | 300 | COCOMO | Intermediate | 3*0.3^1.12
24 | Development of Reporting webpage | Ankita,Hao,Athina | 250 | COCOMO | Intermediate | 3*0.25^1.12
25 | Development of Electronic Doc View Page | Ankita,Hao,Athina | 200 | COCOMO | Int | 3*0.2^1.12
26 | Development of Contractual Requirement page | Ankita,Hao,Athina | 200 | COCOMO | Simple | 2.4*0.2^1.05
27 | Page for potential customers | Ankita,Hao,Athina | 300 | COCOMO | Int | 3*0.3^1.12
| Oracle CRM Development | Ankita,Hao,Athina | 2850 | COCOMO | Intermediate | 3*2.85^1.12
28 | Search/Query Mgmt Module | Ankita,Hao,Athina | 350 | COCOMO | Intermediate | 3*0.35^1.12
29 | Registered customers,placeholders for potential customers | Ankita,Hao,Athina | 300 | COCOMO | Intermediate | 3*0.3^1.12
30 | Costomer service request module | Ankita,Hao,Athina | 400 | COCOMO | Intermediate | 3*0.4^1.12
31 | Update third party data sources | Ankita,Hao,Athina | 300 | COCOMO | Intermediate | 3*0.3^1.12
32 | Campaign management Module | Ankita,Hao,Athina | 300 | COCOMO | Intermediate | 3*0.3^1.12
33 | CR | Ankita,Hao,Athina | 400 | COCOMO | Intermediate | 3*0.4^1.12
34 | Customer Correspondence Management Module | Ankita,Hao,Athina | 600 | COCOMO | Intermediate | 3*0.6^1.12
35 | Auditing changes to data | Ankita,Hao,Athina | 200 | COCOMO | Intermediate | 3*0.2^1.12
| Test Plan Preperation | Thanos,Jo | NA | Delphi | All agreed | 27
36 | Prep of test plan | Thanos,Jo | NA | Delphi | All agreed | 20
37 | Verification and approval of test plan | Thanos,jo | NA | Delphi | All agreed | 7
38 | Installation of the Developed Systems | Ankita,Hao,Athina | NA | Delphi | All agreed | 2
| Testing Phase | Thanos,Jo | 400 | COCOMO and Delphi | Intermediate | (3*0.4^1.12)+30
39 | Unit Testing | Thanos,Jo | 400 | COCOMO | Intermediate | 3*0.4^1.12
40 | Regretion Testing | Thanos,Jo | NA | Delphi | Intermediate | 7
41 | Integration Testing | Thanos,Jo | NA | Delphi | Intermediate | 3
42 | System Testing | Thanos,Jo | NA | Delphi | Intermediate | 10
43 | Performance/scalability Testing | Thanos,Jo | NA | Delphi | Intermediate | 10
44 | Bug Fixing | Ankita,Hao,Athina | 200 | COCOMO | Intermediate | 3*0.2^1.12
45 | Code Deployment | Ankita | 150 | COCOMO | Intermediate | 3*0.15^1.12
46 | Customer Acceptance Testing and Bug Fixing | Ankita,Hao,Athina,Thanos,Jo | 200 | COCOMO | Intermediate | 3*0.2^1.12
47 | Quality Assurance | Ankita | NA | Delphi | All agreed | 5
48 | Project Documentation | Ankita | NA | Delphi | All agreed | 3